## Sheet1
|  |  | WEEK 1 (Week Commencing 8/3/21) |  |  |  |  | WEEK 2 (WC 15/3/21) |  |  |  |  | WEEK 3 (WC 22/3/21) |  |  |  |  | WEEK 4 (WC 29/3/21) |  |  |  |  | WEEK 5 (WC 5/4/21) |  |  |  |  | WEEK 6 (WC 12/4/21) |  |  |  |  | WEEK 7 (WC 19/4/21) |  |  |  |  | WEEK 8 (WC 26/4/21) |  |  |  |  | WEEK 9 (WC 3/5/21) |  |  |  |  | WEEK 10 (WC 10/5/21) |  |  |  |  | WEEK 11 (WC 17/5/21) |  |  |  |  | WEEK 12 (WC 24/5/21)
Task | Location | Duration | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI | MON | TUE | WED | THU | FRI
RESEARCH (TASK 1) | [60 empty] | #NAME? | #NAME?
Create a NEW Reflective Blog | college | 1 day
Mindmap of Initial Ideas | college | 1 day
Start filling out Production Schedule | college | on going
Decide on your MAIN FMP idea. | college | 2 days
Write Up Marketting Report | college | 1 day
Write Up Genre Research | college | 2 days
Complete Treatment of FMP Idea | college | 3 days
PITCH PRESENTATION (TASK 2)
Prepare Pitch Slideshow | home | 2 days
Present Pitch to Tutor | media room | 1 day
(Blog) Feedback on Pitch | Media room | 1 day
Post recorded feedback on reflective blog | media room | 1 day
PRE-PRODUCTION (TASK 3)
Shot List | college | 1 day
Storyboard (12 panels min) | college | 1 day
Location Recce(s) | home | 1 day
Risk Assessment(s) | home | 1 day
Sign Permission to Film forms | home | 1 day
Write the script/narrative | college | 1 day
Work on 'rough' concepts/designs (posters, character costumes etc) | college | 2 days
Create an Equipment List | college | 1 days
PRODUCTION (TASK 4)
Begin filming/recording for the project. | home | 1 week
Complete filming/pickup shots for the project. | home | 1 week
Screenshot progression use of both Premiere Pro, Audition, Photoshop etc | college | 1 day
Finish producing short film/trailer video piece. | college | 3 days
Finish producing x2 posters | college | 1 day
Finsih producing x2 radio ads | college | 1 day
EVALUATION (TASK 5)
Critique / Feedback notes as evidence and your own thoughts. | college | 1 day
On-going reflective learning experience from start to finish. | college | on going
Final Evaluation of Project | college | 3 days
Annotation of design work elements | college | 2 days
CONTINGENCY PLAN